## Gantt Chart
GANTT CHART TEMPLATE | [6 empty] | Smartsheet Tip ➜ | [5 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
PROJECT TITLE |  | [Project's title] |  |  |  |  | COMPANY NAME | [6 empty] | [Company's name]
PROJECT MANAGER |  | [Project Manager's name] |  |  |  |  | DATE | [6 empty] | 2021-08-17
WBS NUMBER | TASK TITLE | Deliverable | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | PHASE ONE | [12 empty] | PHASE TWO | [9 empty] | PHASE THREE
[7 empty] | M | T | W | R | F | S | S | M | T | W | R | F | S | S | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | S | S | M
1 | Project Conception and Initiation
1.1 | Research on Project Topic |  | 2021-08-17 | 2021-08-18 | 1 | 100% | bar: PHASE ONE T
1.1.1 | Research on Business Cases |  | 2021-08-19 | 2021-08-20 | 1 | 100% | bar: PHASE ONE W
1.2 | Finanize the Project Topic |  | 2021-08-21 | 2021-08-22 | 1 | 100% | bar: PHASE ONE R
1.3 | Research |  | 2021-08-23 | 2021-08-26 | 3 | 40% | bar: PHASE ONE F to PHASE ONE S
1.4 | Literatual review |  | 2021-08-27 | 2021-08-30 | 3 | 10% | bar: PHASE ONE M to PHASE ONE W
1.5 | Project Proposal | Project Proposal | 2021-08-31 | 2021-09-03 | 3 | 10% | bar: PHASE ONE R to PHASE ONE S
2 | Project Detail Design
2.1 | Gathering Data |  | 2021-09-04 | 2021-09-05 | 1 | 50% | bar: PHASE TWO S
2.2 | Analyze Data |  | 2021-09-06 | 2021-09-09 | 3 | 20% | bar: PHASE TWO F to PHASE TWO T
2.3 | Interface Design |  | 2021-09-10 | 2021-09-13 | 3 | 0% | bar: PHASE TWO W to PHASE TWO F
2.4 | Storyboard + Diagram | Prototype draft | 2021-09-14 | 2021-09-17 | 3 | 0% | bar: PHASE TWO M to PHASE TWO W
3 | Project Prototype
3.1 | Setup Platform |  | 2021-09-18 | 2021-09-19 | 1 | 0% | bar: PHASE THREE R
3.2 | Programming |  | 2021-09-20 | 2021-09-30 | 10 | 0% | bar: PHASE THREE F to PHASE THREE R
3.2.1 | Testing |  | 2021-10-01 | 2021-10-03 | 2 | 0% | bar: PHASE THREE F to PHASE THREE M
3.2.2 | Modify and Fine tuning |  | 2021-10-04 | 2021-10-09 | 5 | 0% | bar: PHASE THREE T to PHASE THREE M
3.3 | Develop Report |  | 2021-10-10 | 2021-10-15 | 5 | 0% | bar: PHASE THREE T to PHASE THREE S
3.3.1 | Final Review | Final Project Report | 2021-10-16 | 2021-10-18 | 2 | 0% | bar: PHASE THREE S to PHASE THREE M
Formulas:
DUE DATE = [START DATE]+[DURATION]
START DATE = [DUE DATE, row above]+1